## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
1 | Recruiter Publishes Recruitment Positions | As a Recruiter I want to publish recruitment position information (including position name, responsibilities, requirements, salary, number of hires) in the system So that job seekers can view and apply for corresponding positions in the system | High | 1 | 1. The system provides a position release form that supports filling in required fields such as position name, job responsibilities, job requirements, salary range, number of hires, and deadline 2. The form supports previewing position information and submitting for release after confirmation 3. The status of the published position is "Published" and displayed in the position list on the job seeker side 4. The system gives a clear error prompt when the release fails (e.g., required fields are not filled, format errors) | 5 |  | 2026.3.11 | 2026.3.16
2 | Job Seeker Registers and Logs in to the System | As a Job Seeker I want to complete registration and log in to the system via mobile phone number/email, and modify my personal login password So that I can enter the system to view positions, submit resumes and perform other operations | High | 1 | 1. Supports two registration methods (mobile phone number/email) with verification code validation required 2. The registration password must meet complexity requirements (more than 8 characters, including numbers + letters), and the system verifies it in real time 3. Supports login with mobile phone number/email + password, and also supports quick login with verification code 4. Provides a "Forgot Password" function to reset the password via verification code 5. Jumps to the job seeker's personal homepage after successful login, and gives a clear prompt for login failure | 3 |  | 2026.3.17 | 2026.3.20
3 | Job Seeker Submits Resumes Online | As a Job Seeker I want to fill in/upload my personal resume and submit it for published positions So that I can recommend myself to enterprises and get interview opportunities | High | 1 | 1. The system supports online filling of basic resume information (personal info, educational background, work experience, skills and certificates) 2. Supports uploading resume attachments in PDF/Word format, with the attachment size not exceeding 10M 3. Job seekers can click "Apply Now" for a position and confirm resume information before submission 4. The system gives a prompt after successful submission, and the status of the position in the position list changes to "Applied" 5. The same resume can be submitted for multiple positions, and submission records are viewable in the personal center | 5 |  | 2026.3.20 | 2026.3.25
4 | Job Seeker Saves Favorite Positions | As a Job Seeker I want to save the positions I am interested in and view the favorite list in the personal center So that I can quickly find the positions I care about for subsequent application | Medium | 1 | 1. A "Save" button is available on both the position list and position detail pages, and the position is saved after clicking 2. The button status changes to "Saved" after successful collection, and supports canceling the save 3. The job seeker's personal center has a "My Favorites" section that displays all saved positions 4. The favorite list supports filtering by position name and release time, and resumes can be submitted directly from the favorite list 5. After a position is taken offline, it is marked as "Offline" in the favorite list and cannot be applied for | 2 |  | 2026.3.26 | 2026.3.28