## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
TA1 | Collection intention positions | As a TA applicant I want collect interested TA jobs So that I can view and apply for them later | P2 | 1 | 1. Job details pages support "favorite/unfavorite," with a red marker indicating a saved job. 2. A "My Favorites" section in the user center displays all saved jobs. 3. Saved jobs that have closed or filled will be automatically marked "Expired" with a notification. 4. Batch unsaving is supported, with no limit on the number of saved jobs. | 3 |  | 2026-03-17 | 2026-03-20
MO1 | Job Announcement Released | As a Module OrganiserI want to post announcements for my hired TAsSo that I can send work notices and requirements in time | P1 | 1 | 1. Announcements will only be published to approved users. Announcement content can include text and attachments. 2. After the announcement is published, users will receive a notification via both in-app message and email. 3. Users can view the "read/unread" list of users and send reminders to unread users. 4. Announcements can be edited/deleted; deleted announcements will no longer be viewable on the user's end. | 3 |  | 2026-03-21 | 2026-03-24
AD1 | Manage user accounts | As a School AdminI want to add/delete/edit MO/TA accounts and assign permissionsSo that I can control the system user access | P1 | 1 | 1. Supports batch creation of MO accounts and association with their assigned modules. 2. Allows freezing/unfreezing of TA/MO accounts; frozen accounts cannot log in. 3. Allows modification of user roles (e.g., MO → Admin), with permissions taking effect immediately. 4. All account operation records are searchable, including the operator, time, and content. | 4 |  | 2026-03-26 | 2026-03-30