## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
1 | Admin Views and Balances TA Workload | As an Admin (International School Staff), I want to view the total workload hours of each applicant, So that I can ensure no student exceeds the maximum allowed working hours. | Medium | 3 | 1.The system provides an "Admin Dashboard" interface. 2. The system reads the applications.json file and performs aggregation calculations (Sum) based on Student ID to count the total working hours of positions applied for by each student. 3.The system displays the student's name and their total working hours in a list or chart format on the interface. 4.If a student's total working hours exceed the set threshold (e.g., 20 hours), the system highlights them with a red warning. | 5 |  | 4.5 | 4.1
2 | System Matches Skills between Jobs and Applicants (AI Suggestion) | As an Applicant, I want the system to recommend jobs that match my skills, So that I can find suitable positions quickly. | Low | 4 | 1.The applicant enters their personal skills (e.g., Java, Teaching, Research). 2.The system retrieves both the job-required skills and the applicant's skills. 3.AI/Logic Logic: The system calculates the matching percentage using a simple keyword matching algorithm (or basic NLP logic, such as calculating word frequency overlap). 4.The system displays a "Recommended Jobs" list on the homepage, showing the matching degree (e.g., "80% Match"). | 10 |  | 4.22 | 4.29
3 | Module Organiser Reviews Application List | As a Module Organiser (MO), I want to view a list of all applicants for my published positions along with their basic info and CVs, So that I can review their qualifications. | High | 2 | 1.MO can access a "Review Applications" page specific to each of their published jobs. 2.The system reads data from applications.json and users.csv to display a list of applicants. 3.The list displays key information: Applicant Name, Student ID, Major, Applied Date, and a link to download the CV. 4.Each entry has a "Review" button that leads to a detailed view of the applicant's full profile. 5.If no applications exist, the system displays a "No applicants yet" message. | 5 |  | 3.28 | 4.3
4 | System Sends Status Update Notification to Applicant | As an Applicant, I want to receive a notification (in-app or simulated email) when the status of my application changes, So that I can stay informed about the recruitment progress. | Medium | 2 | 1.When the MO changes the application status (e.g., from "Pending" to "Shortlisted"), the system triggers a notification. 2.File-based Notification Logic: The system updates a notifications.json file or adds a flag in users.csv to record the message. 3.The applicant, upon logging in, sees a "You have new notifications" badge or a message list. 4.Clicking on the notification clears the "unread" status. Notifications include the job title and the new status (e.g., "Your application for [Job] has been Shortlisted"). | 6 |  | 3.26 | 4.3