## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
US-SYS-001 | System Login | As a user (TA/MO/Admin), I want to log in with User ID and password to access role-specific functions securely， so that I can protect my account information and use system features matching my role. | Highest | 1 | 1. Empty User ID/password is rejected. 2. Validate credentials against text/CSV files. 3. Account locked for 5 mins after 3 failed attempts. 4. Unlogged users are redirected to login page. | 3 | Core security feature; aligns with User.login() in UML; Java only; no database | 2026-03-22 | 2026-03-29
US-SYS-002 | System Logout | As any system user (TA/MO/Admin), I want to log out securely and clear my session data from the system, so that I can protect my account security when stepping away from the device | Highest | 1 | 1. "Logout" button in user menu. 2. Clear login state and redirect to login page. 3. Auto-logout after 30 minutes of inactivity. 4. Log logout event for audit. | 3 | Aligns with User.logout() in UML | 2026-03-22 | 2026-03-29
US-TA-001 | Create TA Profile | As a TA, I want to create a personal profile including major and skills, so that the system can identify me and provide matching TA job recommendations. | Highest | 1 | 1. Mandatory fields: Major, Skill List (multi-select), CV Path (TXT/CSV only). 2. Generate unique TA ID. 3. Save data to text/CSV file. 4. Allow view and edit profile. | 3 | Aligns with TA.createProfile() and TA.uploadCV() in UML | 2026-03-22 | 2026-03-29
US-MO-001 | Post TA Job | As a MO, I want to create and publish TA job postings with course, skills, workload and deadline， so that I can recruit qualified TAs for my courses efficiently. | Highest | 1 | 1. Require Course Name, Required Skills, Weekly Workload (1-15hrs), Application Deadline. 2. Generate unique Job ID with default "Open" status. 3. Link to MO ID and save to text/CSV. 4. Job ID/MO ID cannot be modified after posting. | 3 | Aligns with MO.createTAJobs() and Job.postJob() in UML | 2026-03-22 | 2026-03-29
US-TA-002 | Browse Open Jobs | As a TA, I want to view all open (non-expired) TA jobs, so that I can find suitable positions to apply for. | Highest | 1 | 1. Display only "Open" jobs, filter out "Closed" jobs. 2. Show Course Name, Required Skills, Workload, Deadline, "View Details". 3. Support sorting by deadline or workload. 4. Load data instantly from text/CSV files. | 3 | Core functionality for TA application | 2026-03-22 | 2026-03-29
US-TA-003 | Submit Application | As a TA, I want to submit applications for selected open jobs, so that I can participate in the recruitment process of my desired positions. | Highest | 1 | 1. "Apply" enabled only for logged-in TAs and open jobs. 2. Generate unique Application ID linking TA ID and Job ID. 3. Status defaults to "Pending", log apply time. 4. Block duplicate applications (same TA + Job). | 5 | Complex logic linking three core objects | 2026-03-22 | 2026-03-29
US-MO-002 | View Applicants | As a MO, I want to view all applicants for my posted jobs, so that I can screen and evaluate candidates for my TA positions. | Highest | 1 | 1. Only view jobs created by myself (filtered by MO ID). 2. List Name, TA ID, Major, Skills, "View CV" link. 3. Open CV file by clicking link. 4. Sort by application time (newest first). | 5 | Critical for Sprint 2 demo | 2026-03-22 | 2026-03-29
US-TA-007 | TA Submits Resumes Online | As a TA, I want to upload resume documents, and apply for TA positions directly, so that I can complete the application process efficiently | Highest | 1 | 1. Support online resume filling and PDF/Word upload (≤10M). 2. Confirm resume before submission. 3. Show success prompt and update status to "Applied". 4. View application records in personal center. | 5 | From Junyi Yan’s requirement | 2026-03-22 | 2026-03-29
US-MO-003 | Review Applications | As a MO, I want to update application status (Accepted/Rejected) and add review notes, so that I can manage the recruitment process and inform candidates of results. | High | 2 | 1. Select application and confirm Accept/Reject. 2. Update status in text/CSV, log review time and MO ID. 3. Save optional Review Note. 4. Sync status to TA’s "My Applications" in real time. | 5 | Aligns with MO.reviewApplications() in UML | 2026-03-29 | 2026-04-12
US-TA-004 | Check Application Status | As a TA, I want to view status of all submitted applications, so that I can track my application progress in real time. | High | 2 | 1. Show Job Name, Apply Time, color-coded Status. 2. Support filtering by status. 3. View detailed history and review notes. 4. Real-time status update. | 3 | Aligns with TA.checkApplicationStatus() in UML | 2026-03-29 | 2026-04-12
US-AD-001 | View All Jobs (Admin) | As an Admin, I want to view all TA jobs across the school, so that I can monitor the overall TA recruitment situation of the school. | High | 2 | 1. List all jobs (Open/Closed) with Course Name, Posting MO, Status, Applicant Count. 2. Show summary stats (Total Jobs, Total Applicants). 3. Support filtering by status or course. 4. Aggregate data from text/CSV files. | 5 | Aligns with Admin.viewAllTAJobs() in UML | 2026-03-29 | 2026-04-12
US-MO-004 | Edit/Close Job | As a MO, I want to edit open jobs or close them to stop applications, so that I can update job information in time or end recruitment when positions are filled. | High | 2 | 1. Edit only "Open" jobs (skills/workload/deadline). 2. Close job to set status "Closed" and disable applications. 3. Log all changes (time/MO ID), retain edit history. 4. Grey out closed jobs in list. | 3 | Aligns with MO.editTAJobs() and MO.closeTAJobs() in UML | 2026-03-29 | 2026-04-12
US-AD-002 | View TA Workload (Admin) | As an Admin, I want to view total weekly workload of all hired Tas, so that I can balance the workload distribution among TAs reasonably. | High | 2 | 1. Show accepted TAs with ID, Name, Total Weekly Workload. 2. Highlight TAs exceeding 10hrs/week in red. 3. Drill down to view individual job assignments. 4. Auto-calculate data from text/CSV files. | 3 | Aligns with Admin.viewTAWorkload() in UML | 2026-03-29 | 2026-04-12
US-MO-006 | MO Recruitment info publishment | As a MO, I want to publish position info including name, responsibilities, requirements, salary and hires, so that TA applicants can fully understand the position before applying. | High | 2 | 1. Support filling required fields and preview before release. 2. Set status to "Published" after submission. 3. Show clear error messages for invalid input. | 5 | From Junyi Yan’s requirement | 2026-03-29 | 2026-04-12
US-TA-006 | TA Registers and Logs in | As a TA, I want to register and log in using phone number or email, so that I can securely access my account and manage my job applications | Medium | 3 | 1. Support phone/email registration with verification code. 2. Password ≥8 chars (numbers + letters). 3. Support password login and verification code quick login. 4. Forgot password function via verification code. | 3 | From Junyi Yan’s requirement | 2026-04-12 | 2026-05-03
US-TA-008 | TA Saves Favorite Positions | As a TA applicant, I want to save interested TA positions and view my saved jobs list, so that I can easily revisit and apply for positions I find relevant later | Medium | 3 | 1. Save/unsave positions in list and detail pages. 2. Show all saved positions in "My Favorites". 3. Filter saved positions by name and time. 4. Mark offline positions and disable application. | 2 | From Junyi Yan’s requirement | 2026-04-12 | 2026-05-03
US-TA-009 | Favorite Jobs | As a TA applicant, I want to collect and save interested TA jobs to a favorites list, so that I can keep track of positions I want to apply for and avoid missing opportunities | Medium | 3 | 1. Support favorite/unfavorite in job details, mark saved jobs. 2. Show all saved jobs in "My Favorites". 3. Auto-mark closed jobs as "Expired". 4. Support batch unsaving. | 3 | From Weize Hu’s requirement | 2026-04-12 | 2026-05-03
US-MO-007 | Post Job Announcement | As a MO, I want to post official announcements for hired TAs regarding onboarding and job requirements, so that newly hired TAs receive clear information about their roles and next steps | Medium | 3 | 1. Publish only to accepted TAs, support text and attachments. 2. Send in-app and email notifications. 3. View read/unread list and send reminders. 4. Allow edit/delete announcements. | 3 | From Weize Hu’s requirement | 2026-04-12 | 2026-05-03
US-AD-003 | Manage User Accounts | As an Admin, I want to add, delete, and edit MO/TA user accounts and assign appropriate role permissions, so that I can maintain proper access control and user management for the system | Medium | 3 | 1. Batch create MO accounts and link to modules. 2. Freeze/unfreeze accounts (frozen accounts cannot login). 3. Modify user roles, permissions take effect immediately. 4. Log all account operations. | 4 | From Weize Hu’s requirement | 2026-04-12 | 2026-05-03
US-AD-004 | AI Balance Workload | As an Admin, I want to receive AI-generated suggestions to balance TA workload across different courses, so that I can ensure fair workload distribution and optimal resource allocation | Medium | 3 | 1. Identify overloaded and underloaded TAs. 2. Generate actionable reallocation suggestions. 3. Export suggestions as TXT/CSV. 4. Only advisory, no automatic data modification. | 5 | Advanced AI Feature | 2026-04-12 | 2026-05-03
US-MO-005 | Filter Applicants by Skill | As a MO, I want to filter applicants by skill match rate, so that I can quickly screen out candidates who meet the job skill requirements. | Medium | 3 | 1. Filter dropdown (≥80% Match, ≥60% Match). 2. Use same AI logic as TA recommendation. 3. Refresh list to show qualified applicants. 4. Clear filter to restore full list. | 3 | Aligns with MO.filterApplicantsBySkill() in UML | 2026-04-12 | 2026-05-03
US-AD-005 | Deactivate User Accounts | As an Admin, I want to deactivate invalid or expired user accounts (instead of permanent deletion), so that I can maintain data integrity while preventing unauthorized access | Low | 4 | 1. List all users with Active/Inactive status. 2. Set status to Inactive to block login. 3. Log action (Admin ID, time), retain historical data. 4. Allow reactivate accounts. | 3 | Aligns with Admin.deactivateUser() in UML | 2026-05-03 | 2026-05-24
US-AD-006 | Export Recruitment Data | As an Admin, I want to export recruitment data (applications, hires, etc.) as CSV files, so that I can perform offline analysis and generate reports for school management | Low | 4 | 1. Export Jobs, Applications, Workload. 2. Support date range filter. 3. CSV format with clear headers for Excel. 4. Log export action. | 3 | Aligns with Admin.exportRecruitmentData() in UML | 2026-05-03 | 2026-05-24
US-TA-010 | Delete Pending Application | As a TA, I want to delete my own pending applications for TA jobs before they are reviewed, so that I can correct mistakes or withdraw applications for positions I am no longer interested in | Low | 4 | 1. Delete only Pending applications before deadline. 2. Require user confirmation. 3. Remove application from lists and text/CSV file. 4. Log deletion for traceability. | 3 | Supplementary feature | 2026-05-03 | 2026-05-24
US-SYS-003 | Change Password | As any user, I want to modify my password, so that I can enhance the security of my account and prevent unauthorized access. | Low | 4 | 1. Verify old password, new password ≥6 chars. 2. Reject incorrect old password or mismatched new passwords. 3. Save new password to text/CSV. 4. Show success/error feedback. | 3 | Aligns with User.modifyPassword() in UML | 2026-05-03 | 2026-05-24
US-TA-005 | AI Job Recommendation | As a TA, I want AI-recommended jobs based on skill matching, so that I can quickly find positions that match my professional abilities. | Low | 4 | 1. Calculate Skill Match Rate (0-100%). 2. Sort jobs by match rate (descending) with "Recommended" tag. 3. Show matched/missing skills on hover. 4. Auto-update when TA skills change. | 5 | AI Feature; aligns with System_Control.aiSkillMatch() in UML | 2026-05-03 | 2026-05-24