## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
US-SYS-001 | System Login | Allow users (TA/MO/Admin) to log in with User ID and password to access role-specific functions. | Highest | 1 | 1. The login interface requires User ID and password input; empty submission is rejected. | 3 | Core security feature; aligns with User.login() in UML. | 2026-03-07 | 2026-03-30
2. System validates credentials against text/CSV files; redirects to role-specific menu on success or shows an error message on failure.
3. Account is temporarily locked (5 mins) after 3 failed login attempts.
4. Unlogged users are redirected to the login page when accessing protected functions.
US-CORE-001 | Create TA Profile | Enable TA applicants to create a personal profile (major/skills/CV path) for system identification. | Highest | 1 | 1. Profile form includes mandatory fields: Major, Skill List (multi-select), and CV Path (TXT/CSV only). | 3 | Aligns with TA.createProfile() and TA.uploadCV() in UML. | 2026-03-07 | 2026-03-30
2. A unique TA ID (e.g., TA028) is generated upon submission.
3. Data is saved to a text/CSV file; no database is used.
4. The TA can view and edit their profile in the "My Profile" section.
US-CORE-002 | Post TA Job | Allow MOs to create and publish TA job postings (course/skills/workload/deadline) for applicants to view. | Highest | 1 | 1. Job creation form requires: Course Name, Required Skills, Weekly Workload (1-15hrs), and Application Deadline. | 3 | Aligns with MO.createTAJobs() and Job.postJob() in UML. | 2026-03-07 | 2026-03-30
2. A unique Job ID (e.g., JOB028) is generated with status "Open" by default.
3. Job data links to the MO's ID (moId) and is saved to text/CSV.
4. MO cannot modify Job ID or MO ID after posting.
US-CORE-003 | Browse Open Jobs | Allow TA applicants to view a list of all open (non-expired) TA jobs. | Highest | 1 | 1. Job list displays only jobs with status "Open"; filtered out "Closed" jobs. | 3 | Core functionality for TA application; aligns with Job class fields. | 2026-03-07 | 2026-03-30
2. Each job entry shows: Course Name, Required Skills, Workload, Deadline, and "View Details".
3. Simple sorting by deadline (earliest first) or workload (lowest first) is supported.
4. Job details are loaded from text/CSV files instantly.
US-CORE-004 | Submit Application | Enable TAs to submit applications for selected open jobs, generating an application record. | Highest | 1 | 1. "Apply" button is only enabled for logged-in TAs and open/non-expired jobs. | 5 | Complex logic linking three core objects; aligns with TA.applyForJob() and Application.submit(). | 2026-03-11 | 2026-03-30
2. A unique Application ID (e.g., APP02801) is generated, linking TA ID and Job ID.
3. Status defaults to "Pending"; apply time is logged and saved to text/CSV.
4. Duplicate applications (same TA + Job) are blocked.
US-CORE-005 | View Applicants | Allow MOs to view all applicants for their posted jobs and review their profiles/CVs. | Highest | 2 | 1. MOs can only view jobs they created (filtered by MO ID). | 5 | Aligns with MO.viewApplicants() in UML; critical for Sprint 2 demo. | 2026-03-16 | 2026-03-30
2. Applicant list includes: Name, TA ID, Major, Skills, and "View CV" link.
3. Clicking "View CV" opens the TXT/CSV file specified in the TA's profile.
4. List supports sorting by application time (newest first).
US-CORE-006 | Review Applications | Allow MOs to update application status (Accepted/Rejected) and add review notes. | Highest | 2 | 1. MO can select an application and choose "Accept" or "Reject" with confirmation. | 5 | Aligns with MO.reviewApplications() and Application.updateStatus() in UML. | 2026-03-16 | 2026-03-30
2. Status is updated in text/CSV; review time and MO ID are logged.
3. An optional "Review Note" field is saved with the application.
4. Status change is reflected in the TA's "My Applications" page in real time.
US-CORE-007 | Check Application Status | Enable TAs to view the status (Pending/Accepted/Rejected) of all their submitted applications. | Highest | 2 | 1. "My Applications" page displays all applications with Job Name, Apply Time, and Status. | 3 | Aligns with TA.checkApplicationStatus() in UML. | 2026-03-16 | 2026-03-30
2. Status labels are color-coded (Pending: Grey, Accepted: Green, Rejected: Red).
3. Filtering by status (e.g., show only Accepted) is supported.
4. Clicking an application shows detailed history (including notes).
US-CORE-008 | View All Jobs (Admin) | Allow Admin to view all TA jobs across the school to monitor recruitment progress. | Highest | 2 | 1. Admin page lists all jobs (Open/Closed) with Course Name, Posting MO, Status, and Applicant Count. | 5 | Aligns with Admin.viewAllTAJobs() in UML. | 2026-03-16 | 2026-03-30
2. Summary stats (Total Jobs, Total Applicants) are displayed.
3. Filtering by status or course is available.
4. Data is aggregated from text/CSV files.
US-MID-001 | Change Password | Allow users to modify their password after verifying the old one for account security. | High | 1 | 1. Form requires Old Password (verification), New Password (≥6 chars), and Confirm Password. | 3 | Aligns with User.modifyPassword() in UML. | 2026-03-07 | 2026-03-30
2. System rejects if old password is incorrect or new passwords do not match.
3. New password is saved to text/CSV; login requires new password afterward.
4. Success/error feedback is provided.
US-MID-002 | Edit/Close Job | Allow MOs to edit details of open jobs or close them to stop applications. | High | 3 | 1. "Edit" button is only enabled for "Open" jobs; allows modifying skills/workload/deadline. | 3 | Aligns with MO.editTAJobs() and MO.closeTAJobs() in UML. | 2026-03-21 | 2026-03-30
2. "Close" button sets status to "Closed", disabling new applications.
3. All changes are logged (time/MO ID); edit history is retained.
4. Closed jobs are greyed out in the list.
US-MID-003 | AI Job Recommendation | Provide TAs with AI-recommended jobs based on skill matching to find suitable positions quickly. | High | 3 | 1. System calculates a Skill Match Rate (0-100%) between TA skills and job requirements. | 5 | AI Feature; aligns with System_Control.aiSkillMatch() in UML. | 2026-03-21 | 2026-03-30
2. Jobs are sorted by match rate (descending) with a "Recommended" tag.
3. Detailed match info (Matched/Missing skills) is shown on hover.
4. Recommendations update automatically when TA skills are updated.
US-MID-004 | Filter Applicants by Skill | Enable MOs to filter applicants by their skill match rate to quickly identify top candidates. | High | 3 | 1. Applicant list features a filter dropdown (e.g., ≥80% Match, ≥60% Match). | 3 | Aligns with MO.filterApplicantsBySkill() in UML. | 2026-03-21 | 2026-03-30
2. System calculates match rate using the same logic as the TA recommendation feature.
3. List refreshes to show only qualifying applicants.
4. "Clear Filter" button restores the full list.
US-MID-005 | View TA Workload (Admin) | Allow Admin to view the total weekly workload of all hired TAs to check for overloading. | High | 2 | 1. List shows accepted TAs with ID, Name, and Total Weekly Workload. | 3 | Aligns with Admin.viewTAWorkload() in UML. | 2026-03-16 | 2026-03-30
2. TAs exceeding a threshold (e.g., 10hrs/week) are highlighted in red.
3. Admin can drill down to view individual job assignments.
4. Workload data is auto-calculated from text/CSV files.
US-MID-006 | System Logout | Allow users to log out securely, clearing their session. | Medium | 4 | 1. "Logout" button is present in the user menu. | 3 | Aligns with User.logout() in UML. | 2026-03-26 | 2026-03-30
2. Clicking it clears login state and redirects to the login page.
3. Auto-logout activates after 30 minutes of inactivity (optional).
4. Logout event is logged for audit.
US-LOW-001 | AI Balance Workload | Generate AI suggestions to reallocate jobs and balance workload across TAs for fairness. | Medium | 3 | 1. System identifies overloaded and underloaded TAs. | 5 | Advanced AI Feature; aligns with Admin.balanceTAWorkload() in UML. | 2026-03-21 | 2026-03-30
2. Generates actionable suggestions (e.g., "Reassign JOB028 to TA010").
3. Suggestions can be exported as TXT/CSV.
4. Suggestions are advisory only; no automatic data modification.
US-LOW-002 | Deactivate User Accounts | Allow Admin to deactivate invalid/expired user accounts to maintain system security. | Medium | 4 | 1. Admin page lists all users with status (Active/Inactive). | 3 | Aligns with Admin.deactivateUser() in UML. | 2026-03-26 | 2026-03-30
2. "Deactivate" button sets status to "Inactive", preventing login.
3. Action is logged (Admin ID, time); historical data is retained.
4. Accounts can be reactivated.
US-LOW-003 | Export Recruitment Data | Enable Admin to export all recruitment data (jobs/applications/workload) as CSV for offline analysis. | Low | 4 | 1. Export options include Jobs, Applications, and Workload. | 3 | Aligns with Admin.exportRecruitmentData() in UML. | 2026-03-26 | 2026-03-30
2. Date range filter is available to narrow exported data.
3. Output is in CSV format with clear headers compatible with Excel.
4. Export action is logged to prevent unauthorized access.
US-LOW-004 | Delete Application (Pending) | Allow TAs to delete their own pending applications before the deadline. | Low | 4 | 1. "Delete" button is enabled only for "Pending" applications and before the job deadline. | 3 | Supplementary feature based on Weize Hu's version. | 2026-03-26 | 2026-03-30
2. User confirmation is required to prevent accidental deletion.
3. Application is removed from lists and text/CSV file.
4. Deletion is logged for traceability.