## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
S01 | TA Create Applicant Profile | As a TA, I want to create a personal applicant profile with basic info, so that I can register and apply for TA jobs. | P1 | 1 | 1. The system shows a profile form with name, student ID, major and contact fields. | 3 | Data stored in CSV; Java stand-alone app | 13/03/2026 | 15/03/2026
2. The system pops up an error if mandatory fields (student ID/contact) are empty.
3. The profile data is saved to a CSV file successfully after submission.
4. The system warns if the student ID is duplicated.
S02 | TA Upload CV | As a TA, I want to upload my CV file to the system, so that MOs can view my resume for job application. | P1 | 1 | 1. The system has a file upload button for CV (supports doc/txt/pdf). | 3 | CV saved in local folder; Linked to S01 (profile must be created first) | 16/03/2026 | 18/03/2026
2. The system prompts an error if no file is selected or file format is wrong.
3. The uploaded CV is saved in the system folder with TA's student ID as the filename.
4. The TA can see a "Upload Success" prompt after completion.
S03 | MO Post TA Job | As a MO, I want to post a TA job with job details, so that TAs can view and apply for the position. | P1 | 1 | 1. The system shows a job post form with job title, duty and requirement fields. | 3 | Job data stored in CSV; Java stand-alone app | 19/03/2026 | 20/03/2026
2. The system saves the job info to a CSV file after submission.
3. The MO can view all posted jobs in a list after posting.
4. The system prompts an error if the job title field is empty.
S04 | TA Apply for TA Job | As a TA, I want to apply for posted TA jobs, so that I can be considered for the TA position by MOs. | P1 | 1 | 1. The TA can view all posted jobs in a list on the system. | 3 | Application data stored in CSV; Linked to S01 and S03 | 19/03/2026 | 21/03/2026
2. The TA can click an "Apply" button next to each job to submit an application.
3. The application info (TA ID + job ID) is saved to a CSV file.
4. The system shows "Apply Success" and disables the Apply button after application.